## Project Overview
Phase | Goal | Status | Target
Phase 1 | Fast document scan summary | In Progress | Demo Next Week
Phase 2 | Guided extraction run | Pending | Demo Next Week
Phase 3 | Evidence and confidence system | Pending | Demo Next Week
Phase 4 | Question and review loop | Pending | Demo Next Week
Phase 5 | Learning rules and corrections memory | Pending | After Demo
Phase 6 | Robust extraction for all document types | Pending | After Demo
Phase 7 | Production security and scaling | Pending | After Demo
Next query | AI Onboarding Tool Current Phase: Phase 1 Completed Tasks T01 File ingestion T02 Preflight analyzer T03 Document summary engine T04 Summary API endpoint T05 PDF page keyword clustering Current System Status The /scan/summary endpoint is working. PDFs with text layers are clustered correctly into: layout plant_metadata equipment_schedule single_line_diagram PDFs without text layers are detected using: text_layer_present = False Those files will require OCR later. Example behavior Native PDF → topic clustering works Drawing PDF → classified as unknown with text_layer_present=False Next Task T06 Excel sheet scanner Goal Scan Excel files and detect sheet meaning using: * sheet name * header keywords * column structure Target categories plant_metadata equipment_schedule inverter_list tracker_list string_table unknown Environment Python FastAPI backend openpyxl for Excel parsing Expected Output Each detected sheet should return: label sheet_name confidence signals domains content_types entities attributes This will feed the extraction plan in Phase 2. Continue implementation of the Excel sheet scanner.
codes to run for the demo :
python -m uvicorn backend.app:app --reload
{ "root_path": "C:/Users/SaadaSourkhan/Desktop/Work/ai-onboarding/inputs", "sample_pages": 5 }

## Task List
ID | Phase | Task | Description | Status | Priority | Owner | Notes
T01 | Phase1 | File ingestion | Upload documents and assign run id | Done | High | Saadeh
T02 | Phase1 | Preflight analyzer | Detect file type, page count, scan likelihood | Done | High | Saadeh |  |  | planned
T03 | Phase1 | Document summary engine | Scan documents and detect likely sections | Done | High | Saadeh | Demo critical |  |  | 0
T04 | Phase1 | Summary API endpoint | Create /scan/summary endpoint | Done | High | Saadeh |  |  |  | 0
T05 | Phase1 | PDF page keyword clustering | Group pages by topic | Done | High | Saadeh |  | T05 PDF clustering |  | 0
T06 | Phase1 | Excel sheet scanner | Detect sheets and header meaning | Done | High | Saadeh |  | T06 Excel sheet scanner |  | 0
T07 | Phase2 | Extraction orchestrator | Decide parser per file type | Done | High | Saadeh |  | T07 Extraction orchestrator |  | 0
T08 | Phase2 | PDF range extractor | Extract selected page ranges | Done | High | Saadeh |  | T08 PDF range extractor |  | 0
T09 | Phase2 | Excel targeted extractor | Extract selected sheets | in progress | High | Saadeh |  | T09 Excel targeted extractor
T10 | Phase2 | DOCX parser | Extract tables and metadata | Pending | Medium | Saadeh |  | T10 DOCX parser | 3 | 1.5
T11 | Phase3 | Evidence model | Attach page and snippet evidence | Pending | High | Saadeh |  | T11 Evidence model | 4 | 2
T12 | Phase3 | Confidence scoring | Assign score to extracted fields | Pending | Medium | Saadeh |  | T12 Confidence scoring | 3 | 1.5
T13 | Phase4 | User question generator | Ask user when extraction uncertain | Pending | Medium | Saadeh |  | T13 Question generator | 4 | 2
T14 | Phase5 | Learning store | Save user corrections | Pending | Medium | Saadeh |  | T14 Learning store | 4 | 5
T15 | Phase5 | Mapping memory | Remember field mappings | Pending | Medium | Saadeh |  | T15 Mapping memory | 4 | 2
[9 empty] | 22 | 14 | Hours

## Demo Checklist
Demo Step | Feature | Status
Step 1 | Upload mixed documents | Pending
Step 2 | Run fast scan summary | Pending
Step 3 | Show document classification | Pending
Step 4 | Show page ranges detected | Pending
Step 5 | Show Excel sheet detection | Pending
Step 6 | Display recommended extraction plan | Pending
Step 7 | Run guided extraction | Pending
Step 8 | Show extracted fields | Pending
Step 9 | Show evidence and page source | Pending
Step 10 | Ask user questions for low confidence | Pending

## After Demo Plan
Phase | Capability | Description | Priority
Phase A | Better page segmentation | Detect schedules, drawings, title blocks | High
Phase B | Advanced Excel parsing | Header mapping and table structure detection | High
Phase C | Conflict detection | Detect conflicting values across documents | High
Phase D | Catalog mapping | Map fields to OutputV1 schema automatically | High
Phase E | Learning expansion | Improve alias and mapping memory | Medium
Phase F | Azure deployment | Deploy API and services | Medium
Phase G | Monitoring | Add logging and cost tracking | Medium